## SAPUI5 Export
Finding Status | Finding Type | Finding ID | Audit Year | Audit ID | Audit Title | Recommendation ID | Recommendation Type | Recommendation Status | Severity | Finding Title | Finding Description | Category | Recommendation Details | Issue Date | Initial Deadline | Current Deadline | Closing Date | Auditee Submission Date | No. of Deadline Shifts | Relevant Legal Entities | Open for Relevant Legal Entities | Recommendation Owner - Legal Entity | Action Plan Responsible | Responsible Auditor | Audit Lead | Finding Owner - Responsible Board Member | Recom Owner - Responsible Board Member | Recommendation Owner - Division | Recommendation Owner - Area | Recommendation Owner - Managing Director | Recommendation Owner - Business Unit | Management Response | Risk | Recommendation Owner - Head of BU | Board member | Root cause | Finding source | Finding Tag | Reason for extension | Rationale for extension
Draft | FINDING | 2025-078_F01 | 2025 | 2025-078 | Physical security (CBF, CBL) | 2025-078_F01-A01 | Recommendation | Draft | S2 | Lack of escalation process for unimplemented event security controls | Internal Audit noted that the DBG Physical Security Event Risk Management Procedure specifies that, during corporate event preparation, the risk owner (typically the event host) must formally notify Physical Security (FSE) if any mandatory measures from the Event Risk Measure Catalogue (ERMC) are not to be implemented. However, the procedure did not define the escalation or decision-making process for situations where mandatory security controls cannot be implemented during corporate event setup or execution. As a result, there was no formalized workflow for addressing such exceptions, leading to reliance on ad hoc coordination rather than a structured resolution path. | Control Design Effectiveness | - Update the DBG Physical Security Event Risk Management Procedure to define the escalation or decision-making process when mandatory security controls cannot be implemented during corporate event setup or execution. The process should ensure that, if significant residual physical security risk remains, any decision to accept or mitigate the risk is reviewed and validated at an appropriate management level beyond the risk owner, to ensure that high-risk exceptions are transparently assessed and properly managed. - Ensure effective communication of the new process to all relevant stakeholders. |  |  | 2026-05-22 |  |  | 0 | CBL Luxembourg,CI Luxembourg,CS Luxembourg,Clearstream Europe AG,Clearstream Fund CentreSA,Clearstream Holding AG,Deutsche Börse AG,Eurex Clearing AG,Eurex Frankfurt AG,Eurex Repo GmbH,LUXCSD | CBL Luxembourg,CI Luxembourg,CS Luxembourg,Clearstream Europe AG,Clearstream Fund CentreSA,Clearstream Holding AG,Deutsche Börse AG,Eurex Clearing AG,Eurex Frankfurt AG,Eurex Repo GmbH,LUXCSD |  | David Krüger, Moritz Dierkes, Winfried Ries | Xavier Karthaeuser | Xavier Karthaeuser | CHRISTOPH BÖHM(Deutsche Börse AG) | [5 empty] | Physical Security (FSE) agrees with the finding and recommendation, and will implement the recommendation. | Lack of escalation process for unimplemented event security controls increases the risk of unmitigated physical security exposures for attendees and assets, delayed or ad‑hoc decisions, and fragmented accountability. Consequently, there is a heightened risk of operational disruption, safety and security incidents, reputational impact, and non‑compliance with internal governance expectations. This may result in a minor financial impact, material reputational damage or material adverse regulatory impact. |  | CHRISTOPH BÖHM(Deutsche Börse AG),DANIEL BESSE(CS Luxembourg),DANIEL BESSE(Clearstream Holding AG),FABRICE TOMENKO(CI Luxembourg),FRANK ODENDALL(Eurex Repo GmbH),KEVIN HAYES(Clearstream Fund CentreSA),MANFRED MATUSZA(Eurex Clearing AG),MARCO CALIGARIS(LUXCSD),QUINTEN KOEKENBIER(Eurex Frankfurt AG),VOLKER RIEBESELL(Clearstream Europe AG),YANNICK GOINEAU(CBL Luxembourg) | Insufficient policies, procedures and guidelines
Draft | FINDING | 2025-078_F02 | 2025 | 2025-078 | Physical security (CBF, CBL) | 2025-078_F02-A01 | Recommendation | Draft | S2 | Deficiencies in key management process | Internal Audit (IA) identified the absence of a formal process for managing damaged or broken keys, including their storage or destruction, as well as for conducting periodic reviews of both the keys stored in the key safe and the list of personnel authorized to obtain keys. - IA observed in The Square (Luxembourg) that some damaged keys were only bent and could potentially be reused. These keys, along with broken ones, were stored in a plastic bag within an access-restricted room of the Physical Security staff. The issue was also observed in The Cube (Germany), where damaged and broken keys were retained indefinitely in the underground key safe. - IA’s review of the authorized personnel list for obtaining a key in The Cube revealed that it included individuals who should no longer have key-access authorization. This indicated that the list was not regularly reviewed or updated. - During an onsite inspection at The Cube, IA observed that one of five sampled special keys was missing from the safe. Photographic evidence confirming that Physical Security (FSE) had possession of the keys was provided only at a later stage and did not conclusively prove that the keys were in the safe during IA’s inspection. | Control Des. + Control Op. Eff. | - Develop a formal procedure for managing damaged or broken keys. The procedure should e.g., mandate secure storage of all keys and, where destruction is necessary, require execution under dual control with complete and verifiable documentation. - Develop a formal procedure to ensure accurate authorized personnel list to obtain a key. - Conduct a documented ad hoc review of key safes to verify the completeness and accuracy of the inventory. - Develop a formal procedure for periodical review of keys stored in the key safe. - Ensure effective communication of the new processes to all relevant stakeholders. |  |  | 2026-06-19 |  |  | 0 | CBL Luxembourg,CI Luxembourg,CS Luxembourg,Clearstream Europe AG,Clearstream Fund CentreSA,Clearstream Holding AG,Deutsche Börse AG,Eurex Clearing AG,Eurex Frankfurt AG,Eurex Repo GmbH,LUXCSD | CBL Luxembourg,CI Luxembourg,CS Luxembourg,Clearstream Europe AG,Clearstream Fund CentreSA,Clearstream Holding AG,Deutsche Börse AG,Eurex Clearing AG,Eurex Frankfurt AG,Eurex Repo GmbH,LUXCSD |  | David Krüger, Moritz Dierkes, Winfried Ries | Xavier Karthaeuser | Xavier Karthaeuser | CHRISTOPH BÖHM(Deutsche Börse AG) | [5 empty] | Physical Security (FSE) agrees with the finding and recommendation, and will implement the recommendation. | Deficiencies in key management process increase the risk of unauthorized access to restricted areas and assets, potential security breaches, and loss or misuse of keys. This may result in a minor financial impact, material violation of internal and external provisions, or material adverse regulatory impact. |  | CHRISTOPH BÖHM(Deutsche Börse AG),DANIEL BESSE(CS Luxembourg),DANIEL BESSE(Clearstream Holding AG),FABRICE TOMENKO(CI Luxembourg),FRANK ODENDALL(Eurex Repo GmbH),KEVIN HAYES(Clearstream Fund CentreSA),MANFRED MATUSZA(Eurex Clearing AG),MARCO CALIGARIS(LUXCSD),QUINTEN KOEKENBIER(Eurex Frankfurt AG),VOLKER RIEBESELL(Clearstream Europe AG),YANNICK GOINEAU(CBL Luxembourg) | Inadequate Processes
Draft | FINDING | 2025-078_F03 | 2025 | 2025-078 | Physical security (CBF, CBL) | 2025-078_F03-A01 | Recommendation | Draft | S1 | Incomplete Physical Security incident reports | Internal Audit performed a review of Physical Security incident reports and noted: - Incomplete Root Cause Identification: in 93 out of 640 reports, the “Cause/Reason of Incident” field was recorded as “Unknown,” despite the Root Cause Analysis being completed, this indicated a gap in documentation or alignment between analysis and system recording. The frequency of “Unknown” entries varied by vendor: Securitas recorded “Unknown” in 87 of 222 incidents (39%), while WISAG recorded “Unknown” in 6 of 418 incidents (1%). - Incomplete DBAG status review: 14 out of 18 reviewed reports (SR-20250115-013, SR-20241104-194, SR-20240914-151, SR-20241002-167, SR-20241116-203, SR-20241119-205, SR-20240721-175a, SR-20250502-137, SR-20250614-188, SR-20250802-265, SR-20250811-274, SR-20250816-282, SR-20250821-288, SR-20250825-293) remained in an “In Progress” DBAG status for an extended period, despite closure indication in the incident description. This indicated outdated open status of the incidents. The DBG Physical Security – PS - Incident Management Procedure requires that all physical security incidents be documented with a precise and consistent analysis of the root cause, mandates completion of root cause analysis (RCA) before incident closure, and stipulates that incidents must be promptly closed once resolution and RCA are completed. | Control Operating Effectiveness | - Ensure all identified reports with incomplete root cause information (section “Cause or Reason of Incident”) are updated to include the appropriate root causes. - Ensure all identified reports with incomplete DBAG review status are updated to accurately reflect the closure of incidents. - Recommunicate to the relevant stakeholders the mandatory review process to prevent incomplete physical security incident reports. |  |  | 2026-05-22 |  |  | 0 | CBL Luxembourg,CI Luxembourg,CS Luxembourg,Clearstream Europe AG,Clearstream Fund CentreSA,Clearstream Holding AG,Deutsche Börse AG,Eurex Clearing AG,Eurex Frankfurt AG,Eurex Repo GmbH,LUXCSD | CBL Luxembourg,CI Luxembourg,CS Luxembourg,Clearstream Europe AG,Clearstream Fund CentreSA,Clearstream Holding AG,Deutsche Börse AG,Eurex Clearing AG,Eurex Frankfurt AG,Eurex Repo GmbH,LUXCSD |  | David Krüger, Moritz Dierkes, Winfried Ries | Xavier Karthaeuser | Xavier Karthaeuser | CHRISTOPH BÖHM(Deutsche Börse AG) | [5 empty] | Physical Security (FSE) agrees with the finding and recommendation, and will implement the recommendation. | Incomplete or inaccurate documentation of incident root causes may lead to unreliable reporting, ineffective corrective actions, and increased likelihood of recurring incidents. In addition, an incomplete review suggests inadequate follow-up and escalation, weakening incident management governance. This may result in a negligible financial impact, minor violation of internal and external provisions, or limited adverse regulatory impact. |  | CHRISTOPH BÖHM(Deutsche Börse AG),DANIEL BESSE(CS Luxembourg),DANIEL BESSE(Clearstream Holding AG),FABRICE TOMENKO(CI Luxembourg),FRANK ODENDALL(Eurex Repo GmbH),KEVIN HAYES(Clearstream Fund CentreSA),MANFRED MATUSZA(Eurex Clearing AG),MARCO CALIGARIS(LUXCSD),QUINTEN KOEKENBIER(Eurex Frankfurt AG),VOLKER RIEBESELL(Clearstream Europe AG),YANNICK GOINEAU(CBL Luxembourg) | Lack of Awareness
Draft | FINDING | 2025-078_F04 | 2025 | 2025-078 | Physical security (CBF, CBL) | 2025-078_F04-A01 | Recommendation | Draft | S1 | Postal security stamping practice not fully reflected in procedure | The DBG Physical Security Process Handbook – Postal Security requires the “mail x-rayed” stamp only for business mail received in Bertrange (Clearstream’s mailing and archive center). In practice, however, stamping was also applied to mail and parcels delivered directly to the KA post office at The Square, as well as to items received in Eschborn and Frankfurt. This resulted in a discrepancy between the documented procedure and its actual implementation. | Control Design Effectiveness | Update the Physical Security Process Handbook – Postal Security to clearly reflect the actual stamping practices across all relevant locations to ensure consistency and compliance. |  |  | 2026-05-22 |  |  | 0 | CBL Luxembourg,CI Luxembourg,CS Luxembourg,Clearstream Europe AG,Clearstream Fund CentreSA,Clearstream Holding AG,Deutsche Börse AG,Eurex Clearing AG,Eurex Frankfurt AG,Eurex Repo GmbH,LUXCSD | CBL Luxembourg,CI Luxembourg,CS Luxembourg,Clearstream Europe AG,Clearstream Fund CentreSA,Clearstream Holding AG,Deutsche Börse AG,Eurex Clearing AG,Eurex Frankfurt AG,Eurex Repo GmbH,LUXCSD |  | David Krüger, Moritz Dierkes, Winfried Ries | Xavier Karthaeuser | Xavier Karthaeuser | CHRISTOPH BÖHM(Deutsche Börse AG) | [5 empty] | Physical Security (FSE) agrees with the finding and recommendation, and will implement the recommendation. | Postal security stamping practice not fully reflected in procedure presents a risk of inconsistent application of security controls. This may result in a negligible financial impact, minor violation of internal and external provisions, or limited adverse regulatory impact. |  | CHRISTOPH BÖHM(Deutsche Börse AG),DANIEL BESSE(CS Luxembourg),DANIEL BESSE(Clearstream Holding AG),FABRICE TOMENKO(CI Luxembourg),FRANK ODENDALL(Eurex Repo GmbH),KEVIN HAYES(Clearstream Fund CentreSA),MANFRED MATUSZA(Eurex Clearing AG),MARCO CALIGARIS(LUXCSD),QUINTEN KOEKENBIER(Eurex Frankfurt AG),VOLKER RIEBESELL(Clearstream Europe AG),YANNICK GOINEAU(CBL Luxembourg) | Insufficient policies, procedures and guidelines