## Analysis
Date | Activity | Branches | Scope
11.08.2025 | GOS notifed Branch Managers on successful closure of Audit Finding- 2024-022_F02-A01 | Cork (DBAG, CFCL), Prague (CS, ECAG, DBAG), Luxembourg (DBAG) | All branches from STAR project
21.08.2025 | GOS Notified London DBAG branch on necesity to implement Branch Management concept and notifed as well that they are working on guiding principle and report template. GOS at the time delivered branch manager role description and example of org chart. | London (DBAG)
24.11.2025 | GOS Notified London EFAG branch on necesity to implement Branch Management concept and notifed as well that they are working on guiding principle and report template. | London (EFAG)
21.01.2026 | GOS notifed Branch Managers on latest version of the branch reporting template they finalized | Corck (CFCL), Prague (CS, ECAG), | Cork DBAG, Prague DBAG, Luxembourg DBAG missing
21.01.2026 | GOS developed and notified Branch Manager Corck CFCL and CS and ECAG Board Members on “Guiding Principles” document summarizing the design setup agreed with IA | Corck (CFCL), Prague (CS, ECAG), | Cork DBAG, Prague DBAG, Luxembourg DBAG missing
21.01.2026 | GOS notified London EFAG on “Guiding Principles” document summarizing the design setup agreed with IA and branch reporting template | London (EFAG)
22.01.2026 | GOS notified London DBAG on “Guiding Principles” document summarizing the design setup agreed with IA and branch reporting template | London (DBAG)

## Results
Based on the provided data, several inconsistencies in the communication strategy have been identified:
Lack of planned centrilized steeting with defined timelines to the branches outside initial 6 branches from STAR project
The London EFAG branch was notified about the Branch Management concept on November 24, 2025, approximately three months after the London DBAG branch received the same notification on August 21, 2025. | To check during prep meetings with London: Why nothing was done since August, November? Does planned timeline exists?
Incomplete Communication Rollout to branches from STAR project
On January 21, 2026, a notification regarding the latest version of the branch reporting template was not sent to all intended recipients. Communication toward Cork DBAG, Prague DBAG, Luxembourg DBAG is missing | To check with Roberto why?
Inconsistent notification toward branches
On January 21, 2026, multiple communications concerning the "Guiding Principles" document were sent out to different sets of recepiants. CFCL Cork, DBAG and EFAG London Branch Managers received guding principles, while Board Members for Prague CS and ECAG received same communication. | TO check: if dotted reporting line toward board members is missing for brances where BM was notified.